## Sprint 1 Backlog
Story #	Sprint Backlog Item	Task #	Volunteer	Task Details	Initial Effort Estimate (hrs)	New Estimates of Effort remaining at end of					Status
				Day1	Day2	Day3	Day4	Day5	Day6
US001	Creating the login page.	Task 1	Mihir	Write a program for displaying the home page	5	4	4	0				Closed
		Task 2	Shubham	Design the UI for the Home page	4	3	3	1				Closed
		Task 3	Vignesh	Design and create the DB fields	5	3	4	2				Closed
US002	Adding the new customer functionality in the system.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
US003	Adding the edit customer functionality in the system.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		Task 4	Padmesh	Writing the code for the functionality.	4	2	0	0				Closed
US004	Adding the delete customer functionality in the system.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		Task 4	Padmesh	Writing the code for the functionality.	4	2	0	0				Closed
US005	Adding a view status functionality that will allow to view the account status of the existing customers.	Task 1	Mihir	----	6	6	6	6				Open
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		Task n	…	----	--					Closed
US006	Creating a capture account functionality that will display the account details of the customers.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US007	Adding a customer executive functionality through which an existing customer account can be deleted.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US008	Adding a customer executive functionality through which an existing customer account can be viewed.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US009	Adding a search customer functionality in the system.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		Task n	…	----	--
US010	Adding a search account functionality in the system.	Task 1	Mihir	----	6	6	6	6				Open
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US011	Creating a deposit money functionality through which a customer can deposit money in his account.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US012	Creating a withdraw money functionality through which a cashier can deposit money in the customers account.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US013	Creating a transfer money functionality through which a cashier can transfer money in the customers account.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
		…	…	----	--
		Task n	…	----	--
US014	Adding a functionality to print the accounts statement.	Task 1	Mihir	----	6	6	6	6				Closed
		Task 2	Shubham	----	5	5	4	0				Closed
		Task 3	Vignesh	----	5	3	2	2				Closed
US015	Final documentation of this project.	Task 1	Padmesh	Creating the Sprint backog and Burndown chart	6	6	6	6				Closed
		Task 2	Yash	Creating the readme file.	5	5	4	0				Closed

## Sprint 1 Burndown Chart
				Sprint Timeline / Remaining Effort (hrs)

Day0	Day1	Day2	Day3	Day4	Day5	Day6
300	210	190	160	110	65	0