## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | Creating the login page. | Task 1 | Mihir | Write a program for displaying the home page | 5 | 4 | 4 | 0 | 0 | 0 | 0 | Closed
|  | Task 2 | Shubham | Design the UI for the Home page | 4 | 3 | 3 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Vignesh | Design and create the DB fields and logging the user | 5 | 3 | 4 | 2 | 0 | 0 | 0 | Closed
US002 | Adding the new customer functionality in the system. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Database creation and value insertion | 5 | 3 | 2 | 2 |  |  |  | Closed
US003 | Adding the edit customer functionality in the system. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Updating the database with queries | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | Task 4 | Padmesh | Writing the code for the functionality. | 4 | 2 | 0 | 0 |  |  |  | Closed
US004 | Adding the delete customer functionality in the system. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Deleting from the database with required validations | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | Task 4 | Padmesh | Writing the code for the functionality. | 4 | 2 | 0 | 0 |  |  |  | Closed
US005 | Adding a view status functionality that will allow to view the account status of the existing customers. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Open
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Write code for displaying the account status | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | Task n | … | ---- | -- | [6 empty] | Closed
US006 | Creating a capture account functionality that will display the account details of the customers. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Write code for displaying customer status | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US007 | Adding a customer executive functionality through which an existing customer account can be deleted. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Working with database and writing query | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US008 | Adding a customer executive functionality through which an existing customer account can be viewed. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Writing query for viewing the account and displaying it | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US009 | Adding a search customer functionality in the system. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | ---- | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | Task n | … | ---- | --
US010 | Adding a search account functionality in the system. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Open
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Bug fixes if any | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US011 | Creating a deposit money functionality through which a customer can deposit money in his account. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Bug fixes if any | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US012 | Creating a withdraw money functionality through which a cashier can deposit money in the customers account. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Bug fixes if any | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US013 | Creating a transfer money functionality through which a cashier can transfer money in the customers account. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Bug fixes if any | 5 | 3 | 2 | 2 |  |  |  | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
US014 | Adding a functionality to print the accounts statement. | Task 1 | Mihir | ---- | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Shubham | ---- | 5 | 5 | 4 | 0 |  |  |  | Closed
|  | Task 3 | Vignesh | Writing code for account statement and printing it | 5 | 3 | 2 | 2 |  |  |  | Closed
US015 | Final documentation of this project. | Task 1 | Padmesh | Creating the Sprint backog and Burndown chart | 6 | 6 | 6 | 6 |  |  |  | Closed
|  | Task 2 | Yash | Creating the readme file. | 5 | 5 | 4 | 0 |  |  |  | Closed

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
300 | 210 | 190 | 160 | 110 | 65 | 0